## Budget
Phase | Item | Model / SKU | Qty | Unit Cost | Extended Cost | Notes
1 | UniFi Cloud Gateway Ultra | UCG-Ultra | 1 | 109 | 109 | Network controller + gateway
1 | UniFi U6 Pro Access Point (x2) | U6-Pro | 2 | 149 | 298 | Clubhouse WiFi coverage
1 | UniFi 16-port PoE Switch | USW-Pro-16-PoE | 1 | 299 | 299 | Powers cameras and APs
1 | UniFi G5 Dome Camera (x4) | UVC-G5-Dome | 4 | 149 | 596 | Indoor / covered outdoor
1 | UniFi G5 Bullet Camera (x2) | UVC-G5-Bullet | 2 | 119 | 238 | Exterior wide coverage
1 | WOW Fiber Termination | N/A | 1 | 0 | 0 | No cost per community agreement
1 | Cable, conduit, mounting hardware | — | 1 | 250 | 250 | Phase 1 consumables estimate
| Phase 1 Subtotal |  |  |  | 1790
2 | UniFi Access Reader Pro (x2) | UA-Reader-Pro | 2 | 149 | 298 | Clubhouse door entry/exit
2 | UniFi Access Hub | UA-Hub | 1 | 99 | 99 | Access control controller
2 | UniFi G5 Dome Camera (x3) | UVC-G5-Dome | 3 | 149 | 447 | Pool area coverage
2 | UniFi AI Theta Pro Intercom | UAIP-Theta-Pro | 1 | 299 | 299 | Clubhouse visitor intercom
2 | Cable, conduit, mounting hardware | — | 1 | 200 | 200 | Phase 2 consumables estimate
| Phase 2 Subtotal |  |  |  | 1343
3 | UniFi Access Reader Pro (x2) | UA-Reader-Pro | 2 | 149 | 298 | Front and rear gate readers
3 | UniFi Building Bridge (pair) | UBB | 1 | 499 | 499 | Wireless bridge for gate networks (pending LOS check)
3 | UniFi Gate Controller | UA-Gate | 2 | 299 | 598 | Front and rear gate controllers
3 | Cable, conduit, hardware | — | 1 | 165 | 165 | Phase 3 consumables estimate
| Phase 3 Subtotal |  |  |  | 1560
| TOTAL (excl. SC sales tax) |  |  |  | 4693

## Schedule
Phase | Task | Owner | Start Window | End Window | Status | Notes
Pre | Board approval of ARGUS budget | Howard | June 2026 | June 2026 | Pending | Required before ordering
Pre | Equipment ordering | Howard | June 2026 | June 2026 | Pending | Order after board vote
Pre | WOW fiber scheduling with Rico Pruitt | Howard | June 2026 | July 2026 | Pending | Confirm activation date
Pre | Line-of-sight site walk (Phase 3 UBB bridges) | Howard | June 2026 | July 2026 | Pending | Gates may need alternative cabling
Pre | CPS contract termination notice | Howard / GHS | June 2026 | TBD | Pending | Confirm notice period
— | TRAVEL (no work) | — | Jul 1, 2026 | Jul 31, 2026 | BLOCKED | Howard away
1 | UniFi controller + switch installation | Howard | Aug 1 | Aug 5 | Pending
1 | WOW fiber termination at clubhouse | Howard / Rico | Aug 1 | Aug 5 | Pending
1 | Camera mounting and cabling | Howard | Aug 5 | Aug 10 | Pending
1 | WiFi AP installation and tuning | Howard | Aug 10 | Aug 12 | Pending
1 | Phase 1 testing and acceptance | Howard | Aug 12 | Aug 14 | Pending
2 | Pool camera installation | Howard | Aug 15 | Aug 20 | Pending
2 | Door access control (readers, hub) | Howard | Aug 20 | Aug 25 | Pending
2 | Intercom installation | Howard | Aug 25 | Aug 28 | Pending
2 | Phase 2 testing and acceptance | Howard | Aug 28 | Aug 31 | Pending
3 | Gate controller installation | Howard | Sep 1 | Sep 10 | Pending | Pending LOS feasibility
3 | UBB wireless bridge or cabling | Howard | Sep 1 | Sep 10 | Pending | Depends on site walk result
3 | Luke Burke review (data handling) | Howard / Luke | Before go-live | — | Pending | Required for Phase 3
3 | Phase 3 testing and acceptance | Howard | Sep 10 | Sep 20 | Pending
All | GHS access credentials delivered | Howard | Post P1 | — | Pending | Admin login for Sharon/Kevin
All | CPS contract terminated | Howard / GHS | Post P3 | — | Pending | Confirm final termination

## Equipment
Phase | Item | Model | Qty | Unit Cost | Total | Ordered? | Received? | Location
1 | UniFi Cloud Gateway Ultra | UCG-Ultra | 1 | 109 | 109 | No | No | Clubhouse closet
1 | UniFi U6 Pro Access Point | U6-Pro | 2 | 149 | 298 | No | No | Clubhouse ceiling
1 | UniFi 16-port PoE Switch | USW-Pro-16-PoE | 1 | 299 | 299 | No | No | Clubhouse closet
1 | UniFi G5 Dome Camera | UVC-G5-Dome | 4 | 149 | 596 | No | No | Clubhouse interior/entry
1 | UniFi G5 Bullet Camera | UVC-G5-Bullet | 2 | 119 | 238 | No | No | Exterior clubhouse
2 | UniFi Access Reader Pro | UA-Reader-Pro | 2 | 149 | 298 | No | No | Clubhouse doors
2 | UniFi Access Hub | UA-Hub | 1 | 99 | 99 | No | No | Clubhouse closet
2 | UniFi G5 Dome Camera | UVC-G5-Dome | 3 | 149 | 447 | No | No | Pool area
2 | UniFi AI Theta Pro Intercom | UAIP-Theta-Pro | 1 | 299 | 299 | No | No | Clubhouse entry
3 | UniFi Access Reader Pro | UA-Reader-Pro | 2 | 149 | 298 | No | No | Front/rear gates
3 | UniFi Building Bridge (pair) | UBB | 1 | 499 | 499 | No | No | Gate network (LOS req.)
3 | UniFi Gate Controller | UA-Gate | 2 | 299 | 598 | No | No | Front and rear gates
| TOTAL |  |  |  | 4078

## Open Items
# | Item | Owner | Due / Target | Status | Notes
1 | Board vote to approve full ARGUS budget | Howard | June 2026 | Open | Required before equipment order
2 | WOW fiber activation scheduling with Rico Pruitt | Howard | June 2026 | Open | Community agreement in place
3 | Confirm CPS annual contract cost | GHS | June 2026 | Open | Howard to request from Sharon
4 | CPS contract termination notice period | Howard / GHS | June 2026 | Open | Confirm required notice window
5 | Line-of-sight site walk for Phase 3 UBB bridges | Howard | Pre-install | Open | Gates may need direct cabling instead
6 | Luke Burke review of resident/vehicle data handling | Howard / Luke Burke | Pre-Phase 3 | Open | Disclosure and liability review required
7 | GHS admin credentials setup in UniFi | Howard | Post Phase 1 | Pending | Sharon and Kevin Bragman
8 | Board viewer access in UniFi | Howard | Post Phase 1 | Pending | All five board members
9 | CPS contract termination and final billing | Howard / GHS | Post Phase 3 | Pending | Confirm termination process
10 | Documentation and as-built notes | Howard | Post Phase 3 | Pending | Store in ARGUS folder