Project ARGUS

River Shoals HOA  |  Security Infrastructure Modernization

Project name: In Greek myth, Argus Panoptes was a giant with a hundred eyes, the ever watchful guardian who never slept. The name fits a project whose purpose is community-wide visibility and access control across the clubhouse, pool, and both gates, all owned and managed by the board itself.

Project Summary

| Community | River Shoals HOA, Simpsonville SC (280+ lots) |
| --- | --- |
| Objective | Replace vendor-managed (CPS) cameras, gate access, and RFID with board-owned Ubiquiti UniFi infrastructure |
| Total Budget | Approx. $8,497 before SC sales tax (equipment only; labor self-performed) |
| Installation Lead | Howard Rapp, President (operates identical UniFi ecosystem at personal residence) |
| WOW Fiber | Available at clubhouse at no installation cost under existing community agreement |
| Hands-on Start | Early August 2026 (deferred until after July 1-31 travel) |
| Attorney Review | Luke Burke to be consulted before implementing any resident-to-vehicle movement correlation |

Phase Overview

| Phase | Name | Scope | Budget | Labor |
| --- | --- | --- | --- | --- |
| 1 | Clubhouse Core | Cameras (indoor/outdoor), WiFi APs, WOW fiber termination, UniFi Network Server | ~$3,565 | ~14 hrs |
| 2 | Pool and Door Access | Pool cameras, clubhouse door RFID/access control, intercom | ~$2,372 | ~12 hrs |
| 3 | Vehicle Gates | Front and rear gate controllers, vehicle detection, visitor management (pending line-of-sight investigation for UBB wireless bridges) | ~$2,560 | ~13 hrs |
| Total |  |  | ~$8,497 | ~39 hrs |

Installation Schedule

| Window | Phase | Activities |
| --- | --- | --- |
| June 2026 | Pre-installation | Board approval, equipment ordering, WOW fiber coordination with Rico Pruitt |
| July 1-31, 2026 | No work | Howard traveling. No installation activities. |
| Early August 2026 | Phase 1 | Clubhouse cameras, WiFi APs, UniFi controller, WOW fiber termination |
| Mid-Late August 2026 | Phase 2 | Pool cameras, door access control, intercom installation |
| September 2026 | Phase 3 | Gate controllers and vehicle detection (pending line-of-sight feasibility for wireless bridges) |

System Access and Roles

All access credentials and system documentation will be stored in the ARGUS project folder and maintained by the board, not the management company or any vendor.

| Person / Role | Access Level | Notes |
| --- | --- | --- |
| Howard Rapp (President) | Super Admin | System owner and installer |
| GHS (Sharon / Kevin Bragman) | Admin | Day-to-day monitoring and access management |
| Ruth Jansen (Treasurer) | Viewer | Read-only for audit and financial oversight |
| Board Members (Allison, Dave, Maynard, M. Broskie) | Viewer | Incident review as needed |

Open Items and Prerequisites

| Item | Owner | Status |
| --- | --- | --- |
| Board vote to approve full ARGUS budget | Howard / Board | Pending |
| WOW fiber activation at clubhouse | Howard / Rico Pruitt | Community agreement in place; scheduling TBD |
| Line-of-sight investigation for Phase 3 wireless bridges (UBB) at front and rear gates | Howard | Pending site walk |
| GHS to confirm current annual CPS contract cost | GHS | Pending |
| Luke Burke review of resident-to-vehicle movement data handling | Howard / Luke Burke | Required before Phase 3 go-live |
| CPS contract termination notice period confirmed | Howard / GHS | Pending |

Project ARGUS  |  River Shoals HOA Security  |  Confidential Board Document